## Slide 1: Hall D APEL Update
Hall D Commissioning (Elton Smith)
  Tagger/Hall on same PSS (Kelly Mahoney, email Nov 1)
  Substantial effort to SCMB, change req to next ARR
  Hall D/Tagger enclosure PSS functional ~Jan 2014
  Todd will review Hall D ops procedures with Mike McCaughan
RF signals to hall (Tomasz Plawski)
  7/8” heliax from MCC to hall (cable cost ~$4200)
  Questions about alternate clocking for separator upgrade
Alex has requested steering angles/pos ranges at radiator
  Todd evaluating beamline optics
Schedule:
  Todd walking beamline weekly to evaluate installation progress
  Acc-I, II, III commissioning schedules on next slides

## Slide 2: Acc-I
Objectives
  CW beam to inline dump (injector), tune beam (<8uA) to 2R
  Beam through all C100s, rebuilt 1A/2A arcs
  Check out hardware, optics tools, model, applications, etc
Schedule has shifted a bit (cryo delays)
  130 keV beam commissioned in injector as of Nov 11
  Downshift to hot checkout, RF commissioning to Dec 2
New Acc-I Schedule
  Operations: Dec 2 to Dec 16, Jan 10 to Feb 7
  Holiday break: Dec 16 to Jan 10

## Slide 3: Acc-II
Objectives
  3-pass spin-up, optics checkout to BSY
  Hall A checkout
  5.5-pass spin-up, optics checkout to Hall D if feasible
Hall D Transport Review: Jan 16
Acc-II Accelerator Readiness Review (ARR): Jan 28
Acc-II Schedule
  3-pass, Hall A: Feb 28-Apr 18, SAD-II: Apr 18-24
  5.5-pass spin-up, Hall D initial beam: Apr 24-June 7
  Serious concerns about higher arc box PS delivery schedule
  Elton et al investigating split PSS of tagger enclosure, hall

## Slide 4: Box Supplies and Other Issues
FY14 budget may not support 20 weeks of FY14 ops
There is some possibility that first Hall D beam gets moved to Acc-III (Fall 2014)
Even in the most optimistic scenario (Freyberger)
  ~1 uA tune mode beam to Hall D tagger dump in spring
  Transport line hardware, optics checkout

## Slide 5: Acc-III
Objectives
  Full energy checkout with two halls, initial operations
  Initial Hall D radiator, detector checkout
Acc-III Accelerator Readiness Review (ARR): March 1 (?)
Acc-III Schedule
  Sep 22-Dec 19 2014
  Hall D beam: Nov 3-Dec 5
  May include deferred Acc-II activities
  Hall and tagger enclosure presumably secured

## Slide 6: Beamline Installation
All magnets in place
  LCW, electrical hookups in progress
Vacuum pipe installed
  Through CEBAF NL, after first vertical bends to shield wall upstream of radiator
Instrumentation in place
  SEE BPMs on beamline but not cabled yet
  nA BPM hardware on schedule for Acc-III
Overall beamline installation on schedule
  Not driving schedule compared to, e.g., box supply delivery

## Slide 7: Hall D Beamline Photos

## Slide 8: Tagger Magnet Mapping